## Sheet1
Test Case ID | Test Description | Tester | Start Date | End Date | Status
TC_001 | Test login functionality for registered users: Ensure that only registered users can log in and access the system with valid credentials | Fernando Lopez | 2024-10-16 | 2024-10-17 | Not Started
TC_002 | Test account creation and registration process: Verify that new users can create an account and register successfully | Reece Slade | 2024-10-16 | 2024-10-17 | Not Started
TC_003 | Test security features (input validation and sanitization): Validate that the system prevents SQL injection and other malicious attacks through form inputs | Fernando Lopez | 2024-10-18 | 2024-10-19 | Not Started
TC_004 | Test database transaction handling: Ensure database transactions (for booking, modifying, or canceling) are completed successfully without data loss | Reece Slade | 2024-10-18 | 2024-10-19 | Not Started
TC_005 | Test system’s response to invalid inputs during booking: Ensure that invalid inputs (e.g., incorrect dates, missing fields) are handled gracefully | Fernando Lopez | 2024-10-20 | 2024-10-21 | Not Started
TC_006 | Test reminder notifications for bookings: Ensure reminders are sent based on correct timings (e.g., 1 day before the booking) | Reece Slade | 2024-10-20 | 2024-10-21 | Not Started
TC_007 | Test session timeout and user inactivity: Validate that the system logs out inactive users after a certain period | Fernando Lopez | 2024-10-22 | 2024-10-23 | Not Started
TC_008 | Test multiple concurrent user logins: Ensure the system handles multiple users logging in simultaneously without issues | Reece Slade | 2024-10-22 | 2024-10-23 | Not Started
TC_009 | Test booking modification conflicts: Ensure proper error handling when multiple users attempt to modify the same booking simultaneously | Fernando Lopez | 2024-10-24 | 2024-10-25 | Not Started